## Sprint 1
User Story | TO DO | In Progress | Impediment | To Verify | Done
1. Customer Login, Admin Login, Admin Approval[Sunil Kumar] | 1.1 Develop repositories,services,controllers for customer login 1.2 Develop the angular components for customer login 1.3 Integrate Front end and back end | Developing repositories,business models,services,controllers for customer , admin dashboard |  | Customer dashboard and its methods | Admin component and its methods
2. Transaction History,Create account page[Harsha Patil] | 2.1 Develop repositories,services,controllers for customer login 2.2 Develop the angular components for customer login 1.3 Integrate Front end and back end | Developing Frontend for create account component and validating the forms |  |  | Creating and Validating the Registration Component
3. User Credentials [Manikandan] | 3.1 Develop repositories,services,controllers for fund transfer 3.2 Develop the angular components for fund transfer 3.3 Integrate Front end and back end | Developing repositories,Businessmodels for Credentials tables and Maintaing the changes in Database |  | Controllers for User Credentials | Database and Business for User credentials